## Robert Mann
Task | Date | Hours Completed | TOTAL HOURS WORKED
Team Meeting to discuss Pre-Alpha Goals | 2024-10-26 | 2 | 103
Researching app development frameworks | 2024-10-26 | 2
Researching Beeware development methods/walking through beeware tutorials to get a feel for the environment | 2024-10-27 | 2
Discussing and drawing up plans for UI design ideas with Adam | 2024-10-29 | 1
Initialized App workspace with beeware | 2024-10-31 | 1
Worked on home page UI design | 2024-11-02 | 4
Researched Toga design strategies and UI customization techniques | 2024-11-02 | 2
Researched bluetooth connection strategies for mobile apps | 2024-11-04 | 2
Worked on implementing bluetooth connection | 2024-11-04 | 3
Worked on write up, video demo, and pre alpha submission | 2024-11-05 | 3
Minor UI tweaks and bug fixes | 2024-11-16 | 3
Researched bluetooth libraries for python | 2024-11-16 | 2
Implemented and Tested PyBluez functionality on BeeWare | 2024-11-19 | 3
Researched and attempted GUI developer tools and frameworks | 2024-11-19 | 3
Implemented navbar and button functionality with routing | 2024-11-20 | 6
Modified home page UI design and map display | 2024-11-21 | 4
Minor UI tweaks and bug fixes | 2024-11-24 | 2
Implemented bluetooth and profile page functionality | 2024-11-25 | 4
Worked on prototype write up and presentation preparation | 2024-11-26 | 2
Researched bluetooth libraries for android studio | 2024-01-05 | 3
Conducted introductions to android studio development | 2024-01-07 | 2
Redesigned existing UI for android studio | 2024-01-11 | 3
Ran app tests to verify proper functionality | 2024-01-12 | 2
Stakeholder/Group Meeting | 2024-01-16 | 1
Researched bluetooth implementation via MIT app inventor | 2024-01-20 | 2
Created simple app to verify bluetooth connectivity | 2024-01-21 | 2
Researched MIT app inventor development stategies and techniques | 2024-01-22 | 3
Recreated simple UI design for new app build | 2024-01-24 | 2
Implemented navigation bar, bluetooth list display, and profile page elements | 2024-01-25 | 3
Worked on alpha test plan/finalizing alpha build | 2024-01-27 | 4
Conducted testing methods outlined in the alpha test plan | 2024-02-08 | 4
Worked on bug fixes/quality of life improvement | 2024-02-09 | 5
Updated UI design | 2024-02-12 | 4
Improved crash response handling and allows for specified numbers to call | 2024-02-17 | 4
Worked with Adam to accomplish bluetooth crash signal reception | 2024-02-22 | 5
Finalized beta build and all related submission requirements. | 2024-02-25 | 3

## Adam King
Task | Date | Hours Completed | TOTAL HOURS WORKED
Brainstorming… | 2024-10-26 | 2 | 102
Team Meeting to discuss Pre-Alpha Goals | 2024-10-26 | 2
Researching app development frameworks | 2024-10-26 | 2
Researching Beeware development methods/beeware tutorials | 2024-10-27 | 2
Discussing and drawing up plans for UI design ideas | 2024-10-29 | 1
Initialized App workspace with beeware | 2024-10-31 | 1
Worked on home page UI design | 2024-11-02 | 4
Researched Toga design strategies and UI customization techniques | 2024-11-02 | 1
Researched gps tracking and location map libraries | 2024-11-04 | 1
Implemented coordinate-based, interactable, location map in the app | 2024-11-04 | 3
Researched bluetooth library possibilities/tutorials | 2024-11-19 | 3
Attempted bluetooth implementation | 2024-11-21 | 4
Attempted live gps tracking | 2024-11-22 | 2
Attempted bluetooth implementation | 2024-11-24 | 3
Researched kivy as alternate solution to beeware/attempted bluetooth through kivy | 2024-11-25 | 4
Resumed beeware implementation/attempted bluetooth implementation/completed report | 2024-11-26 | 9
Android studio bluetooth research | 2024-01-05 | 3
Implemented basic android studio app | 2024-01-07 | 2
Attempted bluetooth implementation | 2024-01-11 | 4
Ran app tests to verify proper functionality | 2024-01-12 | 2
Stakeholder/Group Meeting | 2024-01-16 | 1
MIT app inventor research | 2024-01-20 | 1
Created simple app to test bluetooth/location storing | 2024-01-21 | 2
Researched MIT app inventor dev tutorials | 2024-01-22 | 3
Implemented storage for user data using FirebaseDB | 2024-01-24 | 2
Implemented map and location tracking | 2024-01-25 | 3
Worked on alpha test plan | 2024-01-27 | 4
Finalizing alpha build | 2024-01-28 | 5
Conducted testing methods outlined in the alpha test plan | 2024-02-08 | 4
Bug Fixes and quality of life updates | 2024-02-09 | 5
Implented connection to phone via bluetooth | 2024-02-12 | 4
Implemented signal reception through bluetooth | 2024-02-17 | 5
Worked with Rob to complete bluetooth crash signal reception | 2024-02-22 | 5
Finalized beta build and all related submission requirements. | 2024-02-25 | 3

## Evan Chang
Task | Date | Hours Completed | TOTAL HOURS WORKED
Brainstorming… | 2024-10-26 | 2 | 109.75
Researched and ordered ultrasonic and bluetooth peripherals | 2024-10-26 | 3
Initial Development of Ultrasonic drivers | 2024-10-26 | 2
Github Setup | 2024-11-03 | 1
Work on sensor drivers | 2024-11-03 | 4
Wrote I2C driver and created gyroscope and accelerometer tests | 2024-11-05 | 4
Worked on I2C and ultrasonic sensor, write up, and video | 2024-11-05 | 3
Work on generalized drivers for sensor | 2024-11-14 | 3
Fixed UART | 2024-11-17 | 3
Sensor setup with RTOS and LED | 2024-11-20 | 4
Worked on Sensor/IMU algorithm | 2024-11-24 | 4
Fixed CCS setup/git repo on pc | 2024-11-25 | 3
Assembled prototype, work on write up, interfacing with bluetooth | 2024-11-26 | 8.5
Debugging compilation issue | 2024-01-06 | 6
Fixing linker command file | 2024-01-07 | 2
Setup voltage regulator | 2024-01-10 | 1
Work on HC-SR04 ultrasonic sensor | 2024-01-10 | 5
Work on HC-SR04 ultrasonic sensor | 2024-01-11 | 6
Research/ordering new ultrasonic sensor | 2024-01-12 | 2
Setup new ultrasonic sensor (UART attempt) | 2024-01-24 | 4
Setup new ultrasonic sensor (UART attempt) | 2024-01-24 | 4
Setup new ultrasonic sensor (ADC attempt) | 2024-01-26 | 6
Reworking breadboard layout | 2024-01-27 | 1
Watched 3-4 Michael Stapleton Altium Tutorials | 2024-02-01 | 1
First attempt at creating a footprint for PCM component | 2024-02-03 | 5
Tried to add the new part to a design. Did not work. | 2024-02-03 | 1
Watched Altium Academy videos | 2024-02-04 | 2
Research on pad sizes and header sizes | 2024-02-04 | 2
First attempt at creating a footprint for Tiva Launchpad | 2024-02-06 | 2
Researching premade footprints for all parts (Only found Tiva) | 2024-02-07 | 1
Learning how to import/importing Tiva library | 2024-02-07 | 0.5
Going to Home Depot/Harbor Freight to research/purchase calipers | 2024-02-15 | 0.5
Taking precision measurements of parts with calipers | 2024-02-15 | 0.75
Second attempt at creating a footprint for PCM component | 2024-02-19 | 5
Creating footprint for voltage regulator | 2024-02-16 | 2
Creating footprint for ESP-32 breakout board | 2024-02-17 | 3
Creating footprint for LV-MaxSonar-EZ sensor | 2024-02-17 | 1
Creating symbols for PCM, regulator, ESP32, and MaxSonar | 2024-02-17 | 1
Added parts to schematic, made some connections | 2024-02-17 | 0.5

## Bradley Hertle
Task | Date | Hours Completed | TOTAL HOURS WORKED
Brainstorming… |  | 2 | 101
hardware programming research & setup | 2024-10-31 | 0.5
cont. hardware programming research & setup | 2024-11-02 | 1.5
basic blink program working on TIVA | 2024-11-02 | 0.5
working on bluetooth example (it works) | 2024-11-02 | 4
Got caught up on github repo and hardware programming | 2024-11-03 | 3.5
Researched & ordered ESP32s, debugged the HC05 some more. | 2024-11-05 | 7
Setup espressif IDF on vscode | 2024-11-16 | 1.5
Got blink example working, had issues with espressif idf paths | 2024-11-17 | 1.5
Researching Bluetooth on ESP32 and playing around with example codes, got a basic external interrupt to work. | 2024-11-17 | 5
Researched BTLE and got basic BLE working on the ESP32 using NimBLE | 2024-11-25 | 6
Connected the BTLE app to the external interrupt and used an external DAD board to change bluetooth output. | 2024-11-26 | 6
Worked with Evan and Jack to make the prototype and connect the ESP32 to their TIVA. We had trouble with the TIVA producing a high voltage of 1.8V, not high enough for the ESP32. Fixed it with some MOSFET logic | 2024-11-26 | 6
Talked about power source | 2024-01-09 | 1
Researched & purchased power source | 2024-01-10 | 4
Setup power source | 2024-01-16 | 1
BLE R&D, figuring out requirements for phone pairing | 2024-01-16 | 3
Vbat reading & ESP ADC research | 2024-01-17 | 3
Switched to Bluedroid framework for more complex BLE and got android pairing to work | 2024-01-25 | 5
Helmet assembly and ESP integration, more BLE dev | 2024-01-27 | 6
BLE data sending and app connection | 2024-01-28 | 10
I2S DAC research, ordered 3 PCM5102 breakout boards | 2024-02-05 | 3
Recieved the chips and did research on the I2S protocol | 2024-02-12 | 3
PCB design discussion w/ Evan, more i2s research | 2024-02-13 | 2
Research on how BT speakers work, A2DP required | 2024-02-18 | 2
Got example A2DP project to recieve audio from iPhone | 2024-02-21 | 3
Connected PCM chip to ESP and played with its features | 2024-02-21 | 5
Added A2DP project to crash detection | 2024-02-22 | 2
Revisited PCB design with Evan to add/edit signals | 2024-02-22 | 1
Met with Jack to combine blindspot hardware w/ esp | 2024-02-23 | 1
Measured current draw of our board setup | 2024-02-23 | 1

## Jack Rea
Task | Date | Hours Completed | TOTAL HOURS WORKED
Team Meeting to discuss Pre-Alpha Goals | 2024-10-26 | 2 | 102
Brainstorming/research | 2024-10-27 | 0.5
Initial creation of GitHub repo and project board | 2024-10-29 | 1.5
Brainstorming session | 2024-10-31 | 1
Researching ultra sonic sensor with TIVA | 2024-10-31 | 2
Full integration of github with project space | 2024-10-31 | 2
Set up Code Composer project with dependencies | 2024-11-03 | 1.5
Began work on ultra-sonic sensor driver/general architecture for demo | 2024-11-03 | 2.5
Wrote/tested accelerometer and gyroscope threads | 2024-11-05 | 3
Tried to get ultra-sonic sensor fully working | 2024-11-05 | 2.5
Contributed to write-up, recorded demo video | 2024-11-05 | 2
Revised ultra-sonic driver | 2024-11-14 | 4
Fixed UART | 2024-11-17 | 3
Sensor setup with RTOS and LED | 2024-11-20 | 4
Tested/developed IMU and blind spot algorithms | 2024-11-24 | 4
Integrated systems/finished report | 2024-11-26 | 10
Talked about power source | 2024-11-09 | 1
Developed plan for beta build | 2024-01-09 | 2
Setup voltage regulator | 2024-01-10 | 1
Work on HC-SR04 ultrasonic sensor | 2024-01-10 | 5
Work on HC-SR04 ultrasonic sensor | 2024-01-11 | 6
Research/ordering new ultrasonic sensor | 2024-01-12 | 2.5
Setup new ultrasonic sensor (UART attempt) | 2024-01-24 | 4
Setup new ultrasonic sensor (UART attempt) | 2024-01-24 | 4
Re-tooled threads in program | 2024-01-26 | 2
Setup new ultrasonic sensor (ADC attempt) | 2024-01-27 | 6
Reworking breadboard layout | 2024-01-27 | 1
Finalized design and system for write-up | 2024-01-28 | 1
Lightly tested sensors | 2024-01-28 | 1
Researched motorcycle crash detection | 2024-02-15 | 2
Researched motorcycle crash detection | 2024-02-16 | 2
Team meeting | 2024-02-20 | 1
Worked on sensor algorithm | 2024-02-21 | 4
Developed crash detection algorithm | 2024-02-22 | 3
Tested for crash detection false positves | 2024-02-22 | 1
Debugged board | 2024-02-23 | 2
Rewired board to fit esp32 | 2024-02-23 | 2
Helped test current across board | 2024-02-23 | 0.5
Finalized beta build, verified requirements | 2024-02-25 | 2.5